## Summary
UHN Accessibility First eLearning Series — Cost Comparison
Prepared for: Jacqueline Silvera, UHN ¦ April 2026
Scope: 1 intro module + 18 guide modules (417 pages / ~58K words source content) ¦ Timeline: 6 months ¦ Audience: UHN staff → TAHSN Phase 2
Grounded in Jacqueline's 'Digitization Guidance': micro-modules (5–7 min), Accessibility Decision Path, role-based entry points, WCAG 2.1 AA, dignity-based & trauma-informed design.
Tier | Description | Target Quality | Total Cost (CAD) | Per Module (CAD) | Grant Fit
Basic | Internal UHN resources only. Articulate Rise templates, SME-authored content, text-to-speech narration, stock imagery. Delivered via UHN LMS. | Compliance-grade | 8000 | 421.0526 | No external funding needed
Medium | External contractors focused on rich MULTIMEDIA content: senior instructional designer, eLearning developer, professional bilingual voiceover, custom illustrations, short scenario videos & motion graphics. WCAG 2.1 AA, SCORM. No custom programming. | Professional, media-rich | 84200 | 4431.5789 | Fits $60K–$120K grant
Premium | BOTH the full eLearning course (19 modules, media-rich, as per Medium tier) AND a companion mobile App (installable PWA) built by an external programmer contractor. The app bundles the Accessibility Decision Path, role-based pathways (Nurse / Admin / Security), and the 'In the Moment' quick-reference tool — installable on staff phones and tablets. | Course + Companion App | 118000 | 6210.5263 | At grant ceiling ($120K)
RECOMMENDATION
Submit the PREMIUM tier (~$118K) as the grant application. It fills the $60K–$120K provincial grant envelope and delivers TWO connected products: the full 19-module eLearning course (media-rich, as per Medium tier) AND a companion mobile App (installable PWA) containing the Accessibility Decision Path, role-based pathways, and the 'In the Moment' quick-reference tool. Together they realize the Digitization Guidance vision in full and create reusable IP for TAHSN Phase 2. If leadership prefers a smaller ask, the MEDIUM tier (~$84K) delivers just the eLearning course with no companion app.
Key assumptions (Medium & Premium):
• Articulate Storyline / Rise license is provided by the eLearning developer contractor (not a separate budget line).
• Project management is handled internally by UHN (not billed to the project).

## Basic Tier
TIER 1 — BASIC (Internal Only)
Category | Line Item | Qty / Units | Unit Cost (CAD) | Subtotal (CAD)
Content | SME time — UHN clinicians / accessibility leads (content review, scripting) | 120 | 0 | 0
Content | Instructional design (internal UHN staff time, if available) | 80 | 0 | 0
Platform | Articulate Rise 360 license (if not already held by UHN) | 1 | 1500 | 1500
Platform | Stock imagery & icon library subscription (6 mo) | 1 | 600 | 600
Media | Text-to-speech narration (AI voices) | 1 | 500 | 500
Media | Basic graphics / layout (internal) | 1 | 0 | 0
QA | WCAG 2.1 AA internal review | 1 | 0 | 0
QA | Accessibility audit tool subscription (6 mo) | 1 | 800 | 800
LMS | Deployment on UHN existing LMS | 1 | 0 | 0
Contingency | Contingency (licenses, overage) | 1 | 4600 | 4600
TOTAL |  |  |  | 8000

## Medium Tier
TIER 2 — MEDIUM (Multimedia-Heavy, No Custom Programming)
Category | Line Item | Qty / Units | Unit Cost (CAD) | Subtotal (CAD)
Instructional Design | Senior instructional designer — chunk 417-page source, scripting, storyboards (18 days) | 18 | 1200 | 21600
eLearning Development | Articulate Storyline / Rise developer — build 19 modules with branching scenarios (contractor provides own license) | 19 | 1100 | 20900
Multimedia — Voiceover | Professional bilingual (EN/FR) voiceover — per module | 19 | 400 | 7600
Multimedia — Visuals | Custom illustrations & iconography (diverse, intersectional imagery) | 1 | 5500 | 5500
Multimedia — Video | Short scenario videos with actors (3 key modules) | 3 | 2500 | 7500
Multimedia — Motion | Motion graphics & animated explainers (5 modules) | 5 | 800 | 4000
Multimedia — Audio | Captions, audio description, sound design across all modules | 19 | 150 | 2850
Platform & Tools | Stock media, icon library, font licenses | 1 | 1200 | 1200
Accessibility QA | External WCAG 2.1 AA audit + remediation pass | 1 | 3500 | 3500
Accessibility QA | User testing with persons with disabilities (6 sessions, honoraria) | 6 | 250 | 1500
LMS Integration | SCORM packaging, UHN LMS deployment & smoke testing | 1 | 3000 | 3000
Contingency | Contingency (~6%) | 1 | 5050 | 5050
TOTAL |  |  |  | 84200

## Premium Tier
TIER 3 — PREMIUM (eLearning Course + Companion Mobile App)
Category | Line Item | Qty / Units | Unit Cost (CAD) | Subtotal (CAD)
Instructional Design | Senior ID — chunk 417-page source + app/course spec collaboration (20 days) | 20 | 1200 | 24000
eLearning Development | Articulate developer — 19 modules with branching scenarios (contractor provides own license) | 19 | 900 | 17100
Multimedia — Voiceover | Professional bilingual (EN/FR) voiceover | 19 | 400 | 7600
Multimedia — Visuals | Custom illustrations, iconography, brand system (shared between course & app) | 1 | 4500 | 4500
Multimedia — Video | Short scenario videos with actors (2 key modules) | 2 | 2500 | 5000
Multimedia — Motion | Motion graphics & animated explainers (4 modules) | 4 | 800 | 3200
Multimedia — Audio | Captions, audio description, sound design across all modules | 19 | 150 | 2850
Companion App | External programmer contractor — app architecture, installable PWA setup, auth, offline support | 1 | 5000 | 5000
Companion App | External programmer contractor — 'Accessibility Decision Path' feature (branching decision-tree) | 1 | 13000 | 13000
Companion App | External programmer contractor — role-based pathway feature (Nurse / Admin / Security entry points) | 1 | 6000 | 6000
Companion App | External programmer contractor — 'In the Moment' quick-reference feature (bookmarkable scenarios) | 1 | 6000 | 6000
Companion App | UX / UI design for companion app (mobile-first, WCAG 2.1 AA) | 1 | 4500 | 4500
Companion App | App testing, deployment & store/PWA launch | 1 | 2500 | 2500
Platform & Tools | App hosting (Year 1) + domain + SSL | 1 | 1500 | 1500
Accessibility QA | External WCAG 2.1 AA audit (course + companion app) | 1 | 3500 | 3500
Accessibility QA | Lived-experience user testing (10 sessions, honoraria + facilitation) | 10 | 300 | 3000
LMS Integration | SCORM packaging, UHN LMS deployment, app–LMS SSO integration | 1 | 4000 | 4000
Contingency | Contingency | 1 | 4750 | 4750
TOTAL |  |  |  | 118000

## Companion App Scope
Companion Mobile App — Scope (Premium Tier Only)
Custom programming is introduced ONLY in the Premium tier. It is packaged as a single installable companion app (PWA) that sits alongside the eLearning course. Medium and Basic tiers deliver only the course.
Component | Description | Timeline | Budget (CAD)
App Architecture & PWA Setup | Installable Progressive Web App scaffolding, authentication (UHN SSO-compatible), offline support, cross-device sync, analytics. | 4 weeks | 5000
Accessibility Decision Path (feature) | Branching decision-tree translating the 'What's happening? / What do you notice? / What does the person need? / What can you adapt?' flow into a guided in-app experience. Output: suggested action, policy alignment, escalation guidance. | 7 weeks | 13000
Role-Based Pathways (feature) | Landing experience routing Nurse / Admin / Security to role-specific scenarios and entry points. Integrates with the other app features. | 3 weeks | 6000
'In the Moment' Quick-Reference (feature) | 'I need help now' screen: bookmarkable scenarios, 30-second summaries, quick search. Optimized for mobile and tablet. | 4 weeks | 6000
UX / UI Design | Mobile-first, WCAG 2.1 AA accessible design system for the app. Reuses the illustrations and iconography created for the course. | Parallel | 4500
Testing, Deployment & Launch | QA, accessibility testing, PWA install flow, launch/enrolment for UHN staff. | 3 weeks | 2500
TOTAL COMPANION APP | All six components delivered within the 6-month project timeline. | Within 6 mo | 37000

## Modules & Timeline
Module List & 6-Month Timeline
# | Module | Phase | Month | Notes
0 | Intro: Accessibility at UHN (orientation) | Foundations | Month 1 | Overview, why this matters, navigation
1 | Introduction to Accessibility & Guiding Principles | Foundations | Month 1
2 | Perceptions, Attitudes & Barriers | Foundations | Month 1
3 | Vision Disabilities | Understanding | Month 2
4 | Sensory, Hearing & Communication Disabilities | Understanding | Month 2
5 | Physical Disabilities & Mobility | Understanding | Month 2
6 | Mental Health Disabilities | Understanding | Month 3
7 | Intellectual, Developmental & Learning Disabilities | Understanding | Month 3
8 | Non-Visible Disabilities | Understanding | Month 3
9 | Aging, Disability & Intersectionality | Applied Practice | Month 4
10 | Engaging with Confidence & Respect | Applied Practice | Month 4
11 | Animals in Healthcare & Public Spaces | Applied Practice | Month 4
12 | Support Persons | Applied Practice | Month 4
13 | Assistive Devices: Access, Safety & Dignity | Applied Practice | Month 5
14 | Communication & Information Accessibility | Applied Practice | Month 5
15 | Neurodiversity & Sensory Regulation | Applied Practice | Month 5
16 | Trauma-Informed Accessibility | Applied Practice | Month 5
17 | Accessibility in Crisis & De-Escalation | Applied Practice | Month 6
18 | Legislation, WCAG 2.1 & Ongoing Practice | Applied Practice | Month 6 | Final: UAT, launch, handoff